## Project weekly checklist
Task | Priority | Owner | Status | End date | Note
Study Javascript | low priority | Chandler | Completed | 2025-02-07
Study Javascript | low priority | George | Completed | 2025-02-07
Study Javascript | low priority | Monda | Completed | 2025-02-07
Study Javascript | low priority | Alien | Completed | 2025-02-07
Study Javascript | low priority | Batyrkhan | Completed | 2025-02-07
Complete setting up the GitHub | low priority | Chandler | Completed | 2025-02-07
Complete setting up the GitHub | low priority | George | Completed | 2025-02-07
Complete setting up the GitHub | low priority | Monda | Completed | 2025-02-07
Complete setting up the GitHub | low priority | Alien | Completed | 2025-02-07
Complete setting up the GitHub | low priority | Batyrkhan | Completed | 2025-02-07
#1 Group meeting | high priority | everyone | Completed | 2025-01-24
Sprint #1
Submit a one-page document to Moodle with your team name, team members (with IDs), and a link to the GitHub repository. | high priority | Chandler | Completed | 2025-02-07 | 1. team name 2. team members with ids 3. link to repository
Implement and demo at least one functionality from "User Authentication & Team Management" (e.g., user login). | high priority | everyone | Completed | 2025-02-07 | 1. Implement User’s login (with roles). 2. Functionality for Admin to create teams and assign users to specific channels. Ensure channels are visible to both admins and normal users.
create a folder for minutes | high priority | Chandler | Completed | 2025-02-07
User stories for Sprint 1 | high priority | Resham | Completed | 2025-02-07 | 1. use github issues 2. identify them with the prefix US.##
Task Breakdown | high priority | Resham | Completed | 2025-02-07
Detailed log of each team member's contribution including time spent on each activity (document) | high priority | Chandler | Completed | 2025-02-07
Sprint Plan (task assignments, priorities, risks) | high priority | Resham | Completed | 2025-02-07
README file with project details | high priority | Monda | Completed | 2025-02-07
Design and implement a Sign Up / Log In page | high priority | Alien | Completed | 2025-02-07
Implement user authentication flow | high priority | George | Completed | 2025-02-07
Implement user authentication flow | high priority | Monda | Completed | 2025-02-07
Create a Welcome Page after successful login | high priority | Alien | Completed | 2025-02-07
Implement user data storage (e.g., username and password hashing) | high priority | George | Completed | 2025-02-07
Implement user data storage (e.g., username and password hashing) | high priority | Monda | Completed | 2025-02-07
Design and develop an API for 1. User authentication (sign up / log in) 2. Verification of user credentials | high priority | Chandler | Completed | 2025-02-07
Design and develop an API for 1. User authentication (sign up / log in) 2. Verification of user credentials | high priority | Batyrkhan | Completed | 2025-02-07
#2 group meeting | low priority | everyone | Completed | 2025-01-31
#3 group meeting | low priority | everyone | Completed | 2025-02-06
#4 group meeting | low priority | everyone | Completed | 2025-02-07
Sprint #2
#5 group meeting | low priority | everyone | Completed | 2025-02-14
Implement direct messaging (DM) | high priority | Backend team | Not started | 2025-03-07 | 1. Allow users to send private messages to each other. 2. Ensure conversations are only visible to participants.
Continuous Integration | high priority | Backend team | Not started | 2025-03-07 | Set up the CI pipeline in the repository.
Documentation | low priority | Chandler | Not started | 2025-03-07 | 1. Log contributions and time spent on each activity in the repository. 2. Write acceptance tests and label them correctly in GitHub. 3. Upload meeting minutes.
UI for group text channels | high priority | Frontend team | Not started | 2025-03-07 | 1. Design and implement the UI for group chat. 2. Add moderation features for admins.
UI for direct messaging | high priority | Frontend team | Not started | 2025-03-07 | 1. Create UI for private messaging between users. 2. Ensure smooth user experience and responsiveness.
Assign user stories as GitHub issues. | low priority | Resham | Not started | 2025-03-07

## Github issues #
Issue # | User story/Task title | Story points | Priority | Risk | Owner | Status | Due date | Description | Sprint #
US.1 - User Registration and login page | As a new user, I want to sign up and log in through a user-friendly interface, so that I can securely access ChatHaven | 5 | high |  |  | Completed | 2025-02-07 |  | 1
US.2 - User authentication flow | As a user, I want a secure authentication process, so that my data remains protected when logging in | 5 | high |  |  | Completed | 2025-02-07 |  | 1
US.3 - Welcome page after succesful login | As a logged-in user, I want to see a welcome page, so that I can access features of the website | 3 | medium |  |  | Completed | 2025-02-07 |  | 1
US.4 - Secure User Data Storage | As a developer, I want to securely store user credentials, so that sensitive information like passwords are protected | 8 | high |  |  | Completed | 2025-02-07 |  | 1
US.5 - API for Authentification & Verification | As a developer, I want an API that handles user authentication and credential verification, so that the frontend and backend can communicate securely and efficiently | 5 | high |  |  | Completed | 2025-02-07 |  | 1
Task.1 | Develop UI wireframes - login and sign-up | 3 | medium | low | Stéphanie Geneus | Completed | 2025-02-03 |  | 1
Task.2 | Implement frontend - HTML | 5 | high | medium | Stéphanie Geneus | Completed | 2025-02-03 |  | 1
Task.3 | Set up (jwt) authentication for user sessions | 8 | high | high | George Guirguis | In progress | 2025-02-01 |  | 1
Task.4 | Implement session management(logout and login persistance) | 5 | medium | medium | Monda Bashatly | In progress | 2025-02-02 |  | 1
Task.5 | Handle login errors | 5 | medium | low | Batyrkhan Aliyev | In progress | 2025-02-07 |  | 1
Task.6 | Design the welcome page UI | 5 | medium | low | Stéphanie Geneus | In progress | 2025-02-07 |  | 1
Task.7 | Set up database schema for user data storage | 8 | high | medium | Monda Bashatly | Completed | 2025-02-06 |  | 1
Task.8 | Password Hashing | 5 | medium | high | Chaoran Chen | In progress | 2025-02-06 |  | 1
Task.9 | Create API endpoints for login/signup | 5 | high | medium | Chaoran Chen | In progress | 2025-02-07 |  | 1
Task.10 | Secure API with https & input validation | 5 | high | High | Batyrkhan Aliyev | In progress | 2025-02-07 |  | 1